## Sheet1
CHINA CONSTRUCTION (S.P.) DEVELOPMENT CO PTE LTD |  |  |  | Form No: | EPE-ME-03_1
PROPOSED PARC ESTA CONDOMINIUM |  |  |  | Ref No: | EPE-ME-03_2
ACCEPTANCE CHECKLIST FOR GAS INSTALLATION (Basement & Common Area)
Location / Storey: EPE-ME-01_3 |  |  |  | Grid Ref : | EPE-ME-03_4
Structural Element: EPE-ME-03_5 |  |  |  | Drawing No: | EPE-ME-03_6
Date/Time of Notification: EPE-ME-03_7 |  | Date/Time Inspection Required: |  |  | EPE-ME-03_8
Item | Detail | Y/N/NA | Checked By |  | Approved By
|  |  | Engr/Foreman Date |  | RE/RTO Date
1 | Gas Installation
A | Check pipe material approved by Owner | EPE-ME-03_9
B | Check routing of pipes in accordance to approved plan | EPE-ME-03_10
C | Check size of pipes | EPE-ME-03_11
D | Check pipe support & brackets | EPE-ME-03_12
E | Check installation of pipe sleeve | EPE-ME-03_13
F | Check installation of box up for gas pipe | EPE-ME-03_14
G | Check any physical damage to pipe | EPE-ME-03_15
H | Check fire rating enclosures and air tight for gas pipe. | EPE-ME-03_16
I | Check welding joints and area that do not allowed any joint. | EPE-ME-03_17
J | Check for transition joints between difference gas pipe materials. | EPE-ME-03_18
K | Check for airtight sealing between gas dropper from false ceiling. | EPE-ME-03_19
L | Check for siphon, spool. | EPE-ME-03_20
M | Check for gas pipe gradient and drainage. | EPE-ME-03_21
N | Other | EPE-ME-03_22
N.1 | No Gas Piping at Bedroom wall | EPE-ME-03_23
N.2 | Gas ball valve and electrical point to gas hob is in separate compartment | EPE-ME-03_24
N.3 | Concealed gas piping in the units are marked for easy reference | EPE-ME-03_25
REMARKS:
Checked By: |  | Rectification Checked By: |  |  | Approved By:
China Construction |  | China Construction |  |  | Resident Engineer/RTO
Signature/Name/Date |  | Signature/Name/Date |  |  | Signature/Name/Date